## Plan
| Mar 19-25 | Mar 12- 1 Apr | Apr 2- 8 | Apr 9- 15 | Apr 16 -22
Tasks | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Hardware procurement
Wireless transciever chips(Bharath,Arjun)
micro-controllers(Aishwarya,Jyoti, Ashwath)
All hardware readiness
System specification document
Document the specification for the wireless part(Arjun, Bharath)
Document the specification for the ECU n peripheral part(Aishwarya,Jyoti, Ashwath)
Wireless chip communication readiness
Interface the wireless chip with micro
Distnace measurem algorithm
CAN write to the ECU
Flow chart for the ECU program
ECU activities
CAN read from the ignition using the CAN case
ADC read/SPI read of force sensor
GPIO interface coding
Code the ECU completely
Integrate with the wireless systems
Test the set up
Make the set up necessary for the demo( to be done in college)
Plan for the report